## Slide 1
Bank of America Virginia Commonwealth University Data Science Center
May 13, 2021
Steering Committee Meeting

## Slide 2
Agenda
Program Calendar
Workstream Updates
  Talent Development
  Community Engagement
  Projects
AOB

## Slide 3
2021 Program Calendar

## Slide 4
Talent Development
Goal: Establish Strategic Talent Pathways to Bank of America from VCU and community colleges
- Raise awareness/brand identity across RVA, evolve academic programs
80 applicants
  26 interviews in-progress for summer internship teams(8)
Technology Pathway Program update
Additions to calendar:
  VCU Engineering Career Fair 9/22
  VCU RamHacks sponsorship 9/25 & 9/26
Next Steps
Actions Taken
Coordinate VCU recruitment plan with Charlotte and RVA for next academic year

## Slide 5
Community Engagement: Supporting Tech Achievement for Richmond Students (STARS)
Goal: Support Computer Science (CS) education in Richmond Public Schools (RPS) to build skills that prime students for careers in CS, data science, and related fields.
Actions Taken
Next Steps
Content Work Group (4/26)
Discussed project possibilities and real-world problems for PBLs
Discussed VA CS standards and BOA-valued CS skills for alignment
Mentorship Work Group (4/27)
Developed Career Coach training plan
Distributed Interest Survey
Exploration Work Group (4/28)
Identified needs from RPS/RTC
Realigned to support all RTC aspects
RPS student decisions due June 1
Code Beats returning to RPS
Content
Meet with STEM Academy Teachers (5/20)
Mentorship
Review interest survey results and plan recruitment strategy
Exploration
Redesign work group schedule and strategy

## Slide 6
Goal: Create the first VCU- BOA multi-disciplinary project team; Execute on 9 week Summer Program
Owners: Alfred Reed, Bank of America
Paul Rocheleau, VCU
Student Recruitment: 80 candidates for 10 positions
VCU Leaders/Advisors: Andrew Ilniki - Center for the Creative Economy
Tamar Nadeen - Computer Science
William Benton – DaVinci Center
VCU Support: Rocheleau, Leonard, Sam Kennedy (VCU Technology/ Administration)
Student Selection
Next phase ideation – work program for first month.
Orientation/Opening sessions
Detailed Summer Calendar
Digital ID: Proposed Pathway Forward
Actions Taken
Next Steps

## Slide 7
Sub Categories (Tasks) for Discussion
Student Experience:
Seamless Connection to Valued Apps
Peer Group Support/ Tutoring Network
Links to Food, Financial Svcs (lose the wallet)
Access to facilities/gym/other
Time Management/Access:
Scheduling (class – routines/work - experiences)
  Awareness of Opportunity
Life Ambitions:
Career Building (Badging, Certs, experiences)
Financial Literacy / Planning
Categorize apps, vendors/platforms
  ID 3-5 interface opportunities of value
ID existing tools/systems to create flexible/seamless interfaces
Scheduling/access: diagram personal activities, VCU/RVA Linkages
ID interface / trust issues
9-Week Goals
Front End
Research advanced interface tools
Identify &Map Data Source
Access/Restrictions
Wire Diagrams
Recommendation for ongoing project
  Define value to stakeholders
Research Identification/Permissions tools
Data Collection/Input Opportunities
Map interfaces to consumer banking
Identify Predictive Analytics/Enabling Tech
Back End

## Slide 8
Appendix

## Slide 9
VCU Engineering: Potential Engagement Initiatives